## Master-Detail
FPT SOFTWARE (FSU17-BU6-GIB) | [5 empty] | Update: | 24/6/2015 |  |  | Creator: | XuanDT2
JAPTOOL Project Schedule | [5 empty] | Total | Done ○ | In progress △,▲,★ | Not start ◇ | Start Over ▲ | Finish Over ★ | [20 empty] | Date： 06/24/2015
[6 empty] | 41 | 30 | 10 | 1 | 0 | 6
Summary Information
[7 empty] | 2015-06-17 | 2015-06-25 | 2015-06-17 | 2015-06-24 |  | 2015 | 21 |  | 1 |  | 6 | [14 empty] | Note
No | Lv | Category | Screen | Work | Note | PG | Plan |  | Actual |  | Progress |  | Cost Plan |  | Cost Actual |  | 2015-06-16 | 2015-06-17 | 2015-06-18 | 2015-06-19 | 2015-06-20 | 2015-06-21 | 2015-06-22 | 2015-06-23 | 2015-06-24 | 2015-06-25 | 2015-06-26 | 2015-06-27 | 2015-06-28 | 2015-06-29 | 2015-06-30
[7 empty] | Start | Finish | Start | Finish |  |  | Hours | Days | Hours | Days | 42171 | 42172 | 42173 | 42174 | 42175 | 42176 | 42177 | 42178 | 42179 | 42180 | 42181 | 42182 | 42183 | 42184 | 42185
1
2
3 | 1 | Layout | Home [Chua dang ky] | Design |  | TuyenTV1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
4 |  |  | Home [Da dang ky] | Design |  | TuyenTV1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
5
6 |  |  | Recommend resource | Design |  | DongDL1 | 2015-06-22 | 2015-06-24 | 2015-06-22 |  |  | △
7 |  |  |  | Review |  |  | 2015-06-25 | 2015-06-25 |  |  |  | ◇
8
9 |  | Layout User | Login | Design |  | DuongTD1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
10 |  |  | Register | Design |  | DuongTD1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
11 |  |  | Forgot password | Design |  | DuongTD1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
12 |  |  | Profile | Design |  | DuongTD1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-22 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
13 |  |  | Activate account | Design |  | NamMH | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
14 |  |  | Chang password | Design |  | NamMH | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
15
16 |  |  | Login | Review |  | DongDL1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
17 |  |  | Register | Review |  | DongDL1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
18 |  |  | Forgot password | Review |  | DongDL1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
19 |  |  | Profile | Review |  | DongDL1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-22 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
20 |  |  | Activate account | Review |  | DongDL1 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
21 |  |  | Chang password | Review |  | DongDL1 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
22
23 |  | Layout Library | Library master | Design |  | TuanNT22 | 2015-06-17 | 2015-06-18 | 2015-06-17 | 2015-06-18 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
24 |  |  | Library category | Design |  | TuanNT22 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 100 | ○ | 4 | 0.5 |  |  | 2015-06-19: 4
25 |  |  | Preview Library | Design |  | TuanNT22 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 2015-06-22 | 100 | ○ | 4 | 0.5 |  |  | 2015-06-19: 4
26 |  |  | Thông tin tham khảo chi tiết | Design |  | TuanNT22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
27
28 |  |  | Library master | Review |  | DongDL1 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 100 | ○
29 |  |  | Library category | Review |  | DongDL1 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 100 | ○
30 |  |  | Preview Library | Review |  | DongDL1 | 2015-06-23 | 2015-06-23 | 2015-06-23 |  |  | ★
31 |  |  | Thông tin tham khảo chi tiết | Review |  | DongDL1 | 2015-06-23 | 2015-06-23 | 2015-06-23 |  |  | ★
32
33 |  | Layout Learning | Learning master | Design |  | TuanNT22 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
34 |  |  | Create Learning | Design |  | DuongTD1 | 2015-06-17 | 2015-06-22 | 2015-06-17 | 2015-06-24 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
35 |  |  | Edit Learning | Design |  | DuongTD1 | 2015-06-22 | 2015-06-22 | 2015-06-24 | 2015-06-24 | 100 | ○
36
37 |  |  | Learning master | Review |  | DongDL1 | 2015-06-24 | 2015-06-24 | 2015-06-24 |  |  | △
38 |  |  | Create Learning | Review |  | DongDL1 | 2015-06-24 | 2015-06-24 | 2015-06-24 |  |  | △
39 |  |  | Edit Learning | Review |  | DongDL1 | 2015-06-24 | 2015-06-24 | 2015-06-24 |  |  | △
40
41 |  | Layout Learning detail | Learning master detail | Design |  | DuongTD1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
42 |  |  | Vocabulary content | Design |  | DuongTD1 | 2015-06-23 | 2015-06-23 |  |  |  | ★
43 |  |  | Kanji content | Design |  | DuongTD1 | 2015-06-23 | 2015-06-23 |  |  |  | ★
44 |  |  | Article content (testing) | Design |  | DuongTD1 | 2015-06-23 | 2015-06-23 |  |  |  | ★
45 |  |  | Result group screen | Design |  | DuongTD1 | 2015-06-23 | 2015-06-23 |  |  |  | ★
46
47 |  | Code | Learning (CRUD) | Code |  | DuongTD1 | 2015-06-17 | 2015-06-25 | 2015-06-17 | 2015-06-24 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
48 |  |  | Library master | Code |  | QuyetND2 | 2015-06-17 | 2015-06-25 | 2015-06-17 | 2015-06-24 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
49 |  |  | Library detail | Code |  | QuyetND2 | 2015-06-17 | 2015-06-18 | 2015-06-17 | 2015-06-24 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
50
51 |  | Study | Upload file | Code |  | NamMH | 2015-06-17 | 2015-06-17 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
52
53 |  | Google Analytics | Guide using GA | Document |  | XuanDT2 | 2015-06-17 | 2015-06-17 | 2015-06-17 | 2015-06-17 | 100 | ○ | 8 | 1 | 8 | 1 | 2015-06-17: 8
8
54
55 |  | Document | Review | Document |  | XuanDT2 | 2015-06-18 | 2015-06-19 | 2015-06-18 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-18: 8
56
57 | 2 | Home | Home [Chua dang ky] | Coding
58 |  |  |  | Review
59 |  |  | Home [Chua dang ky] | Coding
60 |  |  |  | Review
61 |  | User | Login | Coding
62 |  |  |  | Review
63 |  |  | Register | Coding
64 |  |  |  | Review
65 |  |  | Forgot password | Coding
66 |  |  |  | Review
67 |  |  | Profile | Coding
68 |  |  |  | Review
69 |  |  | Activate account | Coding
70 |  |  |  | Review
71 |  |  | Chang password | Coding
72 |  |  |  | Review
73
74 |  | Library | Library master | Coding
75 |  |  |  | Review
76 |  |  | Library category | Coding
77 |  |  |  | Review
78 |  |  | Preview Library | Coding
79 |  |  |  | Review
80 |  |  | Thông tin tham khảo chi tiết | Coding
81 |  |  |  | Review
82
83 |  | Learning | Learning master | Coding
84 |  |  |  | Review
85 |  |  | Create Learning | Coding
86 |  |  |  | Review
87 |  |  | Edit Learning | Coding
88 |  |  |  | Review
89 |  |  | Preview detail Learning | Coding
90 |  |  |  | Review
91
Note on S9: Input Start date of schedule

## Setting
Holidays
No. | Day | Note
1 | 2015-02-16 | Nghỉ tết
2 | 2015-02-17 | Nghỉ tết | 8 | Plan | 8 | Actual | 30 | Current Date
3 | 2015-02-18 | Nghỉ tết
4 | 2015-02-19 | Nghỉ tết |  | 0-99% |  | 100% |  | Saturday
5 | 2015-02-20 | Nghỉ tết
6 |  |  | ◇ | Not yet | △ | Open |  | Sunday, Holiday
7
8 |  |  | ★ | finish over | ○ | Done
9
10 |  |  | ▲ | start over
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## use_guide
○ | cong viec da hoan thanh 100%
★ | cong viec da bi over deadline
△ | Cong viec dang thuc hien (dung nhu plan)
◇ | cong viec chua start