## Master-Detail
FPT SOFTWARE (FSU17-BU6-GIB) | [5 empty] | Update: | 24/6/2015 |  |  | Creator: | XuanDT2
JAPTOOL Project Schedule |  |  |  | Total | Done ○ | In progress △,▲,★ | Not start ◇ | Start Over ▲ | Finish Over ★ | [32 empty] | Date： 08/04/2015
|  |  |  | 107 | 96 | 4 | 7 | 0 | 0
Summary Information
[7 empty] | 2015-06-17 | 2015-08-11 | 2015-06-17 | 2015-07-27 |  | 2015 | 0 |  | 0 |  | 6 | [24 empty] | Note
No | Lv | Category | Screen | Work | Note | PG | Plan |  | Actual |  | Progress |  | Cost Plan |  | Cost Actual |  | 2015-06-16 | 2015-06-17 | 2015-06-18 | 2015-06-19 | 2015-06-20 | 2015-06-21 | 2015-06-22 | 2015-06-23 | 2015-06-24 | 2015-06-25 | 2015-06-26 | 2015-06-27 | 2015-06-28 | 2015-06-29 | 2015-06-30 | 2015-07-01 | 2015-07-02 | 2015-07-03 | 2015-07-04 | 2015-07-05 | 2015-07-06 | 2015-07-07 | 2015-07-08 | 2015-07-09 | 2015-07-10
[7 empty] | Start | Finish | Start | Finish |  |  | Hours | Days | Hours | Days | 42171 | 42172 | 42173 | 42174 | 42175 | 42176 | 42177 | 42178 | 42179 | 42180 | 42181 | 42182 | 42183 | 42184 | 42185 | 42186 | 42187 | 42188 | 42189 | 42190 | 42191 | 42192 | 42193 | 42194 | 42195
1 | 1 | Layout | Home [Chua dang ky] | Design |  | TuyenTV1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○
2 |  |  | Home [Da dang ky] | Design |  | TuyenTV1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○
3 |  |  | Servey | Design |  | TuyenTV1 | 2015-06-22 | 2015-06-24 | 2015-06-22 | 2015-06-25 | 100 | ○
4 |  |  |  | Review |  | DongDL1 | 2015-06-25 | 2015-06-25 | 2015-06-25 | 2015-06-25 | 100 | ○
5 |  |  | Recommend resource | Design |  | TuyenTV1 | 2015-06-22 | 2015-06-24 | 2015-06-22 | 2015-06-25 | 100 | ○
6 |  |  |  | Review |  | DongDL1 | 2015-06-25 | 2015-06-25 | 2015-06-25 | 2015-06-25 | 100 | ○
7 |  | Layout User | Login | Design |  | DuongTD2 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○
8 |  |  | Register | Design |  | DuongTD2 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○
9 |  |  | Forgot password | Design |  | DuongTD2 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○
10 |  |  | Profile | Design |  | DuongTD2 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-22 | 100 | ○
11 |  |  | Activate account | Design |  | NamMH | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
12 |  |  | Chang password | Design |  | NamMH | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
13 |  |  | Login | Review |  | DongDL1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○
14 |  |  | Register | Review |  | DongDL1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○
15 |  |  | Forgot password | Review |  | DongDL1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○
16 |  |  | Profile | Review |  | DongDL1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-22 | 100 | ○
17 |  |  | Activate account | Review |  | DongDL1 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
18 |  |  | Chang password | Review |  | DongDL1 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
19 |  | Layout Library | Library all category | Design |  | TuanNT22 | 2015-06-17 | 2015-06-18 | 2015-06-17 | 2015-06-18 | 100 | ○
20 |  |  | Library by category | Design |  | TuanNT22 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 100 | ○
21 |  |  | Library Preview | Design |  | TuanNT22 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 2015-06-22 | 100 | ○
22 |  |  | Thông tin chi tiết | Design |  | TuanNT22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
23 |  |  | Library all category | Review |  | DongDL1 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 100 | ○
24 |  |  | Library by category | Review |  | DongDL1 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 100 | ○
25 |  |  | Library Preview | Review |  | DongDL1 | 2015-06-23 | 2015-06-23 | 2015-06-23 | 2015-06-25 | 100 | ○
26 |  |  | Thông tin chi tiết | Review |  | DongDL1 | 2015-06-23 | 2015-06-23 | 2015-06-23 | 2015-06-25 | 100 | ○
27 |  | Layout Learning | Learning manage | Design |  | TuanNT22 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○
28 |  |  | Create Learning | Design |  | DuongTD2 | 2015-06-17 | 2015-06-22 | 2015-06-17 | 2015-06-24 | 100 | ○
29 |  |  | Edit Learning | Design |  | DuongTD2 | 2015-06-22 | 2015-06-22 | 2015-06-24 | 2015-06-24 | 100 | ○
30 |  |  | Learning manage | Review |  | DongDL1 | 2015-06-24 | 2015-06-24 | 2015-06-24 | 2015-06-25 | 100 | ○
31 |  |  | Create Learning | Review |  | DongDL1 | 2015-06-24 | 2015-06-24 | 2015-06-24 | 2015-06-25 | 100 | ○
32 |  |  | Edit Learning | Review |  | DongDL1 | 2015-06-24 | 2015-06-24 | 2015-06-24 | 2015-06-25 | 100 | ○
33 |  | Layout Learning detail | Learning detail | Design |  | DuongTD2 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○
34 |  |  | Learning detail | Review |  | DongDL1 | 2015-06-25 | 2015-06-25 | 2015-06-25 | 2015-06-25 | 100 | ○
35 |  |  | Vocabulary content | Design | Từng nhóm tự design |  | 2015-06-23 | 2015-06-23 | 2015-06-23 | 2015-06-23 | 100 | ○
36 |  |  | Kanji content | Design | Từng nhóm tự design |  | 2015-06-23 | 2015-06-23 | 2015-06-23 | 2015-06-23 | 100 | ○
37 |  |  | Grammar | Design | Từng nhóm tự design |  | 2015-06-23 | 2015-06-23 | 2015-06-23 | 2015-06-23 | 100 | ○
38 |  |  | Article content (testing) | Design | Từng nhóm tự design |  | 2015-06-23 | 2015-06-23 | 2015-06-23 | 2015-06-23 | 100 | ○
39 |  |  | Result learning screen | Design |  | NamMH | 2015-06-24 | 2015-06-24 | 2015-06-24 | 2015-06-25 | 100 | ○
40 |  |  | Result learning screen | Review |  | XuanDT2 | 2015-06-25 | 2015-06-25 | 2015-06-25 | 2015-06-25 | 100 | ○
41 |  | Code | Learning (CRUD) | Code |  | DuongTD2 | 2015-06-17 | 2015-06-25 | 2015-06-17 | 2015-06-24 | 100 | ○
42 |  |  | Library master | Code |  | QuyetND2 | 2015-06-17 | 2015-06-25 | 2015-06-17 | 2015-06-24 | 100 | ○
43 |  |  | Library detail | Code |  | QuyetND2 | 2015-06-17 | 2015-06-18 | 2015-06-17 | 2015-06-24 | 100 | ○
44 |  | Study | Upload file | Code |  | NamMH | 2015-06-17 | 2015-06-17 | 2015-06-17 | 2015-06-19 | 100 | ○
45 |  | Google Analytics | Guide using GA | Document |  | XuanDT2 | 2015-06-17 | 2015-06-17 | 2015-06-17 | 2015-06-17 | 100 | ○
46 |  | Document | Review | Document |  | XuanDT2 | 2015-06-18 | 2015-06-19 | 2015-06-18 | 2015-06-19 | 100 | ○
47 | 2 | Home | Home [Chua dang nhap] | Coding |  | NamMH | 2015-06-29 | 2015-06-30 | 2015-06-29 | 2015-07-01 | 100 | ○
48 |  |  | Home [Da dang nhap] | Coding | Stop [DongDL1] | DongDL1 | 2015-06-29 | 2015-06-30 | 2015-06-29 | 2015-06-30 | 100 | ○
49 |  |  | Servey | Coding |  | DongDL1 | 2015-07-01 | 2015-07-03 | 2015-07-01 | 2015-07-03 | 100 | ○
50 |  |  | Recommend resource | Coding |  | NamMH | 2015-07-01 | 2015-07-03 | 2015-07-01 | 2015-07-03 | 100 | ○
51 |  | User | Login | Coding |  | TuyenTV1 | 2015-06-29 | 2015-06-29 | 2015-06-29 | 2015-07-01 | 100 | ○
52 |  |  | Register | Coding |  | TuanNT22 | 2015-06-29 | 2015-06-30 | 2015-06-29 | 2015-07-01 | 100 | ○
53 |  |  | Forgot password | Coding | Stop | TuyenTV1 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 100 | ○
54 |  |  | Profile | Coding |  | TuyenTV1 | 2015-07-01 | 2015-07-03 | 2015-07-02 | 2015-07-04 | 100 | ○
55 |  |  | Activate account | Coding | Stop | TuanNT22 | 2015-07-03 | 2015-07-03 | 2015-07-03 | 2015-07-03 | 100 | ○
56 |  |  | Chang password | Coding |  | TuanNT22 | 2015-07-01 | 2015-07-02 | 2015-06-29 | 2015-07-02 | 100 | ○
57 |  | Library | Library all category | Coding |  | QuyetND2 | 2015-06-29 | 2015-06-29 | 2015-07-01 | 2015-06-29 | 100 | ○
58 |  |  | Library by category | Coding |  | QuyetND2 | 2015-06-30 | 2015-06-30 | 2015-07-01 | 2015-06-30 | 100 | ○
59 |  |  | Library Preview | Coding |  | DuongTD2 | 2015-06-29 | 2015-07-01 | 2015-06-29 | 2015-07-02 | 100 | ○
60 |  |  | Thông tin chi tiết | Coding |  | DuongTD2 | 2015-07-02 | 2015-07-03 | 2015-07-02 | 2015-07-03 | 100 | ○
61 |  | Learning | Learning manage | Coding |  |  | 2015-07-03 | 2015-07-04 | 2015-07-03 | 2015-07-04 | 100 | ○
62 |  |  | Learning create | Coding |  | XuanDT2 | 2015-06-29 | 2015-06-30 | 2015-06-29 | 2015-06-30 | 100 | ○
63 |  |  | Edit Learning | Coding |  | XuanDT2 | 2015-07-01 | 2015-07-02 | 2015-07-01 | 2015-07-02 | 100 | ○
64 |  |  | Learning detail | Coding |  | QuyetND2 | 2015-07-01 | 2015-07-02 | 2015-07-01 | 2015-07-02 | 100 | ○
65 |  |  | Vocabulary content | Read doc + define requeiments |  | TuyenTV1 + TuanNT22 | 2015-07-06 | 2015-07-07 | 2015-07-06 | 2015-07-07 | 100 | ○
66 |  |  |  | Coding |  | TuyenTV1 + TuanNT22 | 2015-07-08 | 2015-07-10 | 2015-07-08 | 2015-07-10 | 100 | ○
67 |  |  | Kanji content | Read doc + define requeiments |  | XuanDT2 | 2015-07-06 | 2015-07-07 | 2015-07-06 | 2015-07-07 | 100 | ○
68 |  |  |  | Coding |  | XuanDT2 | 2015-07-08 | 2015-07-10 | 2015-07-08 | 2015-07-10 | 100 | ○
69 |  |  | Grammar | Read doc + define requeiments |  | DongDL1 + NamMH | 2015-07-06 | 2015-07-07 | 2015-07-06 | 2015-07-07 | 100 | ○
70 |  |  |  | Coding |  | DongDL1 + NamMH | 2015-07-08 | 2015-07-10 | 2015-07-08 | 2015-07-10 | 100 | ○
71 |  |  | Article content (testing) | Read doc + define requeiments |  | QuyetND2 + DuongTD2 | 2015-07-03 | 2015-07-03 | 2015-07-03 | 2015-07-03 | 100 | ○
72 |  |  |  | Coding |  | QuyetND2 + DuongTD2 | 2015-07-04 | 2015-07-09 | 2015-07-04 | 2015-07-09 | 100 | ○
73 |  |  | Learning result | Coding |  | QuyetND2 | 2015-07-10 | 2015-07-10 | 2015-07-10 | 2015-07-10 | 100 | ○
74 |  | Vocalbulary | Layout view Vocalbulary | Design |  | DuongTD2 | 2015-07-22 | 2015-07-23 | 2015-07-22 | 2015-07-22 | 100 | ○
75 |  |  | Layout view Vocalbulary | Review |  | DongDL1 | 2015-07-23 | 2015-07-23 | 2015-07-23 | 2015-07-23 | 100 | ○
76 |  |  | Coding view Vocalbulary | Coding |  | TuyenTV1 + TuanNT22 | 2015-07-22 | 2015-07-24 | 2015-07-22 | 2015-07-22 | 100 | ○
77 |  |  | Coding view Vocalbulary | Review |  | DongDL1 | 2015-07-24 | 2015-07-24 | 2015-07-24 | 2015-07-24 | 100 | ○
78 |  |  | Coding Exercise Vocalbulary | Coding |  | TuyenTV1 + TuanNT22 | 2015-07-22 | 2015-07-24 | 2015-07-22 | 2015-07-22 | 100 | ○
79 |  |  | Coding Exercise Vocalbulary | Review |  | DongDL1 | 2015-07-24 | 2015-07-24 | 2015-07-24 | 2015-07-24 | 100 | ○
80 |  |  | Layout Design Exercise Vocalbulary | Design |  | DuongTD2 | 2015-07-22 | 2015-07-23 | 2015-07-22 | 2015-07-22 | 100 | ○
81 |  |  | Layout Design Exercise Vocalbulary | Review |  | DongDL1 | 2015-07-23 | 2015-07-23 | 2015-07-23 | 2015-07-23 | 100 | ○
82 |  |  | Layout Design Exercise Vocalbulary | Design |  | DuongTD2 | 2015-07-22 | 2015-07-23 | 2015-07-22 | 2015-07-22 | 100 | ○
83 |  |  | Layout Design Exercise Vocalbulary | Review |  | DongDL1 | 2015-07-23 | 2015-07-23 | 2015-07-23 | 2015-07-23 | 100 | ○
84 |  | KanJi | Layout view Vocalbulary | Design |  | DuongTD2 | 2015-07-22 | 2015-07-23 | 2015-07-22 | 2015-07-22 | 100 | ○
85 |  |  | Coding view Vocalbulary | Coding |  | TuyenTV1 + TuanNT22 | 2015-07-22 | 2015-07-24 | 2015-07-22 | 2015-07-22 | 100 | ○
86 |  |  | Coding view Vocalbulary | Review |  | DongDL1 | 2015-07-24 | 2015-07-24 | 2015-07-24 | 2015-07-24 | 100 | ○
87 |  |  | Coding Exercise Vocalbulary | Coding |  | TuyenTV1 + TuanNT22 | 2015-07-22 | 2015-07-24 | 2015-07-22 | 2015-07-22 | 100 | ○
88 |  |  | Coding Exercise Vocalbulary | Review |  | DongDL1 | 2015-07-24 | 2015-07-24 | 2015-07-24 | 2015-07-24 | 100 | ○
89 |  |  | Layout Design Exercise Vocalbulary | Design |  | DuongTD2 | 2015-07-22 | 2015-07-23 | 2015-07-22 | 2015-07-22 | 100 | ○
90 |  |  | Layout Design Exercise Vocalbulary | Review |  | DuongTD2 | 2015-07-23 | 2015-07-23 | 2015-07-23 | 2015-07-23 | 100 | ○
91 |  | Speaking | Technical Speaking | Coding |  | ThanhNV9 | 2015-07-22 | 2015-07-24 | 2015-07-22 | 2015-07-22 | 100 | ○
92 |  |  | Speaking coding | Coding |  | ThanhNV9 | 2015-07-27 | 2015-07-29 | 2015-07-27 | 2015-07-27 | 100 | ○
93 |  | Learning | Optimize Learning Workfolow | Coding |  | NamMH | 2015-07-22 | 2015-07-22 | 2015-07-22 | 2015-07-22 | 100 | ○
94 |  |  | Optimize Learning Workfolow | Review |  | DongDL1 | 2015-07-22 | 2015-07-22 | 2015-07-22 | 2015-07-22 | 100 | ○
95 |  | Home | Optimize home after login | Coding |  | DongDL1 | 2015-07-22 | 2015-07-24 | 2015-07-22 | 2015-07-22 | 100 | ○
96 |  | Library | Merge Layout | Coding |  | NamMH | 2015-07-23 | 2015-07-24 | 2015-07-23 | 2015-07-23 | 100 | ○
97 |  |  | Create Multiple language for all layout | Coding |  | DuongTD2 | 2015-08-03 | 2015-08-05 | 2015-08-03 |  | 50 | △
98 |  |  | Create Multiple language for all layout | Review |  | TuyenTV1 | 2015-08-05 | 2015-08-05 |  |  |  | ◇
99 |  |  | Process history for learning | Coding |  | NamMH | 2015-08-04 | 2015-08-05 | 2015-08-04 |  | 50 | △
100 |  |  | Process history for learning | Review |  | TuyenTV1 | 2015-08-05 | 2015-08-05 |  |  |  | ◇
101 |  |  | Fix blank for learning layout | Coding |  | NamMH | 2015-08-06 | 2015-08-06 |  |  |  | ◇
102 |  |  | Fix blank for learning layout | Review |  | TuyenTV1 | 2015-08-06 | 2015-08-06 |  |  |  | ◇
103 |  |  | correct link and workflow all module | Review |  | DongDL1 | 2015-08-05 | 2015-08-07 |  |  |  | ◇
104 |  |  | group book by category | Coding |  | TuyenTV1 | 2015-08-04 | 2015-08-07 | 2015-08-04 |  | 10 | △
105 |  |  | group book by category | Review |  | DongDL1 | 2015-08-07 | 2015-08-07 |  |  |  | ◇
106 |  |  | group book by category | Coding |  | TuyenTV1 | 2015-08-08 | 2015-08-11 | 2015-08-04 |  | 10 | △
107 |  |  | group book by category | Review |  | DongDL1 | 2015-08-11 | 2015-08-11 |  |  |  | ◇
108
109
110
111
112
113
114
115
116
117
118
119
120
121
Note on S9: Input Start date of schedule

## Setting
Holidays
No. | Day | Note
1 | 2015-02-16 | Nghỉ tết
2 | 2015-02-17 | Nghỉ tết | 8 | Plan | 8 | Actual | 30 | Current Date
3 | 2015-02-18 | Nghỉ tết
4 | 2015-02-19 | Nghỉ tết |  | 0-99% |  | 100% |  | Saturday
5 | 2015-02-20 | Nghỉ tết
6 |  |  | ◇ | Not yet | △ | Open |  | Sunday, Holiday
7
8 |  |  | ★ | finish over | ○ | Done
9
10 |  |  | ▲ | start over
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## use_guide
○ | cong viec da hoan thanh 100%
★ | cong viec da bi over deadline
△ | Cong viec dang thuc hien (dung nhu plan)
◇ | cong viec chua start