## Master-Detail
FPT SOFTWARE (FSU17-BU6-GIB) | [5 empty] | Update: | 24/6/2015 |  |  | Creator: | XuanDT2
JAPTOOL Project Schedule | [5 empty] | Total | Done ○ | In progress △,▲,★ | Not start ◇ | Start Over ▲ | Finish Over ★ | [20 empty] | Date： 06/25/2015
[6 empty] | 44 | 34 | 10 | 0 | 0 | 8
Summary Information
[7 empty] | 2015-06-17 | 2015-06-25 | 2015-06-17 | 2015-06-25 |  | 2015 | 21 |  | 1 |  | 6 | [14 empty] | Note
No | Lv | Category | Screen | Work | Note | PG | Plan |  | Actual |  | Progress |  | Cost Plan |  | Cost Actual |  | 2015-06-16 | 2015-06-17 | 2015-06-18 | 2015-06-19 | 2015-06-20 | 2015-06-21 | 2015-06-22 | 2015-06-23 | 2015-06-24 | 2015-06-25 | 2015-06-26 | 2015-06-27 | 2015-06-28 | 2015-06-29 | 2015-06-30
[7 empty] | Start | Finish | Start | Finish |  |  | Hours | Days | Hours | Days | 42171 | 42172 | 42173 | 42174 | 42175 | 42176 | 42177 | 42178 | 42179 | 42180 | 42181 | 42182 | 42183 | 42184 | 42185
1
2
3 | 1 | Layout | Home [Chua dang ky] | Design |  | TuyenTV1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
4 |  |  | Home [Da dang ky] | Design |  | TuyenTV1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
5
6 |  |  | Servey | Design |  | TuyenTV1 | 2015-06-22 | 2015-06-24 | 2015-06-22 | 2015-06-25 | 100 | ○
7 |  |  |  | Review |  | DongDL1 | 2015-06-25 | 2015-06-25 | 2015-06-25 |  |  | △
8 |  |  | Recommend resource | Design |  | TuyenTV1 | 2015-06-22 | 2015-06-24 | 2015-06-22 | 2015-06-25 | 100 | ○
9 |  |  |  | Review |  | DongDL1 | 2015-06-25 | 2015-06-25 | 2015-06-25 |  |  | △
10
11 |  | Layout User | Login | Design |  | DuongTD1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
12 |  |  | Register | Design |  | DuongTD1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
13 |  |  | Forgot password | Design |  | DuongTD1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
14 |  |  | Profile | Design |  | DuongTD1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-22 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
15 |  |  | Activate account | Design |  | NamMH | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
16 |  |  | Chang password | Design |  | NamMH | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
17
18 |  |  | Login | Review |  | DongDL1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
19 |  |  | Register | Review |  | DongDL1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
20 |  |  | Forgot password | Review |  | DongDL1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
21 |  |  | Profile | Review |  | DongDL1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-22 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
22 |  |  | Activate account | Review |  | DongDL1 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
23 |  |  | Chang password | Review |  | DongDL1 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
24
25 |  | Layout Library | Library all category | Design |  | TuanNT22 | 2015-06-17 | 2015-06-18 | 2015-06-17 | 2015-06-18 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
26 |  |  | Library by category | Design |  | TuanNT22 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 100 | ○ | 4 | 0.5 |  |  | 2015-06-19: 4
27 |  |  | Library Preview | Design |  | TuanNT22 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 2015-06-22 | 100 | ○ | 4 | 0.5 |  |  | 2015-06-19: 4
28 |  |  | Thông tin chi tiết | Design |  | TuanNT22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 2015-06-22 | 100 | ○
29
30 |  |  | Library all category | Review |  | DongDL1 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 100 | ○
31 |  |  | Library by category | Review |  | DongDL1 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 2015-06-19 | 100 | ○
32 |  |  | Library Preview | Review |  | DongDL1 | 2015-06-23 | 2015-06-23 | 2015-06-23 |  |  | ★
33 |  |  | Thông tin chi tiết | Review |  | DongDL1 | 2015-06-23 | 2015-06-23 | 2015-06-23 |  |  | ★
34
35 |  | Layout Learning | Learning manage | Design |  | TuanNT22 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
36 |  |  | Create Learning | Design |  | DuongTD1 | 2015-06-17 | 2015-06-22 | 2015-06-17 | 2015-06-24 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
37 |  |  | Edit Learning | Design |  | DuongTD1 | 2015-06-22 | 2015-06-22 | 2015-06-24 | 2015-06-24 | 100 | ○
38
39 |  |  | Learning manage | Review |  | DongDL1 | 2015-06-24 | 2015-06-24 | 2015-06-24 |  |  | ★
40 |  |  | Create Learning | Review |  | DongDL1 | 2015-06-24 | 2015-06-24 | 2015-06-24 |  |  | ★
41 |  |  | Edit Learning | Review |  | DongDL1 | 2015-06-24 | 2015-06-24 | 2015-06-24 |  |  | ★
42
43 |  | Layout Learning detail | Learning detail | Design |  | DuongTD1 | 2015-06-17 | 2015-06-19 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
44 |  |  | Vocabulary content | Design |  |  | 2015-06-23 | 2015-06-23 |  |  |  | ★
45 |  |  | Kanji content | Design |  |  | 2015-06-23 | 2015-06-23 |  |  |  | ★
46 |  |  | Article content (testing) | Design |  |  | 2015-06-23 | 2015-06-23 |  |  |  | ★
47 |  |  | Result learning screen | Design |  | NamMH | 2015-06-24 | 2015-06-24 | 2015-06-24 | 2015-06-25 | 100 | ○
48 |  |  | Result learning screen | Review |  | XuanDT2 | 2015-06-25 | 2015-06-25 | 2015-06-25 | 2015-06-25 | 100 | ○
49
50 |  | Code | Learning (CRUD) | Code |  | DuongTD1 | 2015-06-17 | 2015-06-25 | 2015-06-17 | 2015-06-24 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
51 |  |  | Library master | Code |  | QuyetND2 | 2015-06-17 | 2015-06-25 | 2015-06-17 | 2015-06-24 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
52 |  |  | Library detail | Code |  | QuyetND2 | 2015-06-17 | 2015-06-18 | 2015-06-17 | 2015-06-24 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
53
54 |  | Study | Upload file | Code |  | NamMH | 2015-06-17 | 2015-06-17 | 2015-06-17 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-17: 8
55
56 |  | Google Analytics | Guide using GA | Document |  | XuanDT2 | 2015-06-17 | 2015-06-17 | 2015-06-17 | 2015-06-17 | 100 | ○ | 8 | 1 | 8 | 1 | 2015-06-17: 8
8
57
58 |  | Document | Review | Document |  | XuanDT2 | 2015-06-18 | 2015-06-19 | 2015-06-18 | 2015-06-19 | 100 | ○ | 8 | 1 |  |  | 2015-06-18: 8
59
60 | 2 | Home | Home [Chua dang ky] | Coding
61 |  |  |  | Review
62 |  |  | Home [Chua dang ky] | Coding
63 |  |  |  | Review
64 |  | User | Login | Coding
65 |  |  |  | Review
66 |  |  | Register | Coding
67 |  |  |  | Review
68 |  |  | Forgot password | Coding
69 |  |  |  | Review
70 |  |  | Profile | Coding
71 |  |  |  | Review
72 |  |  | Activate account | Coding
73 |  |  |  | Review
74 |  |  | Chang password | Coding
75 |  |  |  | Review
76
77 |  | Library | Library all category | Coding
78 |  |  |  | Review
79 |  |  | Library by category | Coding
80 |  |  |  | Review
81 |  |  | Library Preview | Coding
82 |  |  |  | Review
83 |  |  | Thông tin chi tiết | Coding
84 |  |  |  | Review
85
86 |  | Learning | Learning manage | Coding
87 |  |  |  | Review
88 |  |  | Create Learning | Coding
89 |  |  |  | Review
90 |  |  | Edit Learning | Coding
91 |  |  |  | Review
92 |  |  | Learning detail | Coding
93 |  |  |  | Review
94
Note on S9: Input Start date of schedule

## Setting
Holidays
No. | Day | Note
1 | 2015-02-16 | Nghỉ tết
2 | 2015-02-17 | Nghỉ tết | 8 | Plan | 8 | Actual | 30 | Current Date
3 | 2015-02-18 | Nghỉ tết
4 | 2015-02-19 | Nghỉ tết |  | 0-99% |  | 100% |  | Saturday
5 | 2015-02-20 | Nghỉ tết
6 |  |  | ◇ | Not yet | △ | Open |  | Sunday, Holiday
7
8 |  |  | ★ | finish over | ○ | Done
9
10 |  |  | ▲ | start over
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## use_guide
○ | cong viec da hoan thanh 100%
★ | cong viec da bi over deadline
△ | Cong viec dang thuc hien (dung nhu plan)
◇ | cong viec chua start